## contract development roles
Contract/Grant Development Roles
***This document helps users to identify their role and the roles of others within the contract/grant development process. Using the filters you can search for one or a group of specific titles/roles to find the responsbibilites and actions associated with each phase of the process. Please note, filters do not work when the parts of the process are collapsed.***
| TASK | Responsible | Approve | Consult | Inform | Notes
|  | Responsible for the decision/task | Must approve a decision before it can be implemented or moving on to the next step. | Must be consulted by the responsible entity prior to a decision or as part of the task. Agreement not required. | Need to be informed of the final decision or task. No formal role in the decision or task.
1 | Part 1. Pre-Planning
1.1 | Program preplanning about idea | Program/Project Manager | Division Leadership | Technical Staff | Division Leadership | Division Leadership role is APPROVE if funding is not yet approved, otherwise it is INFORM. Dept. of Admin, Fiscal Coordinator, PCA Signers, and Contractor/Grantee roles may be CONSULT or have NO ROLE, determined on a case-by-case basis.
Contract Unit-Specialist
Fiscal Coordinator
PCA signers
Contractor/Grantee
1.2 | Funding (validity) check conversation | Program/Project Manager |  | Division Leadership | Contract Unit-Specialist
Fiscal Coordinator
1.3 | Look at FAQ/Risk Triage | Program/Project Manager |  | Contract Unit-Specialist
1.4 | Decide whether or not to proceed | Program/Project Manager |  | Division Leadership | Technical Staff
2 | Part 2. Request Contract Assistance
2.1 | If solicitation is anticipated, cease related communications with potential Contractors/Grantees | Program/Project Manager
Technical Staff
Division Leadership
Contract Unit-Specialist
2.2 | Prepare/Submit contract request form | Program/Project Manager |  | Fiscal Coordinator |  | Fiscal Coordinator role may be CONSULT or have NO ROLE, determined on a case-by-case basis.
2.3 | Confirm funding source; approve request |  | Division Leadership | Fiscal Coordinator | Program/Project Manager | Fiscal Coordinator role may be CONSULT or have NO ROLE, determined on a case-by-case basis.
2.4 | Verify funding source |  | Fiscal Coordinator |  | Program/Project Manager
2.5 | Approve concept |  | PCA Signer |  | Program/Project Manager
2.6 | Assign request to contract specialist | Contract Unit-Supervisor |  |  | Program/Project Manager
2.7 | Accept assignment in workflow | Contract Unit-Specialist |  |  | Program/Project Manager
3 | Part 3. Kickoff / Determine Approach
3.1 | Review request; do background work | Contract Unit-Specialist
3.2 | Engage in kick off discussion | Contract Unit-Specialist |  | Program/Project Manager |  | Technical Staff and Division Leadership roles may be CONSULT or have NO ROLE, determined on a case-by-case basis.
Technical Staff
Division Leadership
3.3 | If known, encourage Contractors/Grantees to get set up in SWIFT (establish account and e-signature) | Program/Project Manager |  |  | Contractor/Grantee
Contract Unit-Specialist
3.4 | Execute risk triage | Program/Project Manager |  | PCA signers |  | PCA Signers role may be CONSULT or have NO ROLE, determined on a case-by-case basis.
3.5 | Determine if RFP is required | Contract Unit-Specialist |  | Program/Project Manager | Program/Project Manager | Program/Project Manager role may be CONSULT or INFORM, determined on a case-by-case basis. Division Leadership, PCA Signers and Contract Unit-Mentor roles may be CONSULT or have NO ROLE, determined on a case-by-case basis.
Division Leadership
PCA signers
Contract Unit-Mentor
4 | Part 4. Solicitation (if required)
4.1 | Determine if RFP/Quick Call/RFGA is required | Contract Unit-Specialist |  | Program/Project Manager
Division Leadership
Contract Unit-Mentor
4a. | Part 4a. Develop Solicitatoin
4a.1 | Create Solicitation Team | Program/Project Manager |  | Solicitation Team | Contract Unit-Specialist | Solicitation Team may include Division Leadership
Division Leadership
4a.2 | Sign confidentiality agreement | Program/Project Manager |  |  | Contract Unit-Specialist | Division Leadership must sign confidentiality agreement if they are to be informed or consulted
Solicitation Team
Division Leadership
4a.3 | Discuss scope | Program/Project Manager |  | Contract Unit-Specialist |  | Division Leadership role may be CONSULT or have NO ROLE, determined on a case-by-case basis.
|  | Solicitation Team |  | Division Leadership
4a.5 | Draft Solicitation scope and summary | Program/Project Manager |  | Solicitation Team |  | Division Leadership role may be CONSULT or have NO ROLE, determined on a case-by-case basis.
Contract Unit-Specialist
Division Leadership
4a.6 | Draft Solicitation template and sample contract | Contract Unit-Specialist |  | Contract Unit-Mentor | Solicitation Team | Contract Unit-Mentor and Program/Project Manager roles may be CONSULT or NO ROLE, determined on a case-by-case basis. Solicitation Team and Division Leadership roles may be INFORM or have NO ROLE, determined on a case-by-case basis.
|  |  |  | Program/Project Manager | Division Leadership
4a.7 | Compile list of potential Contractors/Grantees to be contacted. | Program/Project Manager |  | Contract Unit-Specialist |  | Division Leadership role may be CONSULT or have NO ROLE, determined on a case-by-case basis.
|  | Solicitation Team |  | Division Leadership
4a.8 | Final review by Solicitation Team | Program/Project Manager | Division Leadership |  | Contract Unit-Specialist | Division Leadership approval at discretion of Division Leadership
Solicitation Team
4b. | Part 4b. Approve and Post Solicitation
4b.1 | Upload complete Solicitation packet into SWIFT, if appropriate | Contract Unit-Specialist
4b.2 | Mentor approval |  | Contract Unit-Mentor | Contract Unit-Specialist | Program/Project Manager
4b.3 | PCA Approver/Signer approval |  | PCA Approver/Signer |  | Program/Project Manager
Contract Unit-Specialist
4b.4 | If PT RFP, Dept. of Administration approval |  | Dept. of Admin. |  | Program/Project Manager
Contract Unit-Specialist
4b.5 | Post on Web, and SWIFT, if applicable | Contract Unit-Specialist |  |  | Program/Project Manager
Proposer/Applicant
4b.6 | Communicate on program website and other sources, if desired | Program/Project Manager |  | Contract Unit-Specialist | Proposer/Applicant
4b.7 | Review proposal and submit questions, if any. | Proposer/Applicant |  |  | Program/Project Manager
Contract Unit-Specialist
4b.8 | Receive questions, share w Solcitation Team | Contract Unit-Specialist |  |  | Program/Project Manager | IN MOST CASES, questions are received and shared by Contract Unit-Specialist. Exceptions will be addressed in the Grant Framework, under development.
|  | Program/Project Manager |  |  | Contract Unit-Specialist
4b.9 | Develop responses. | Contract Unit-Specialist | Contract Unit-Specialist | Contract Unit-Mentor |  | Responses to RFP process related questions are developed by Contract Unit-Specialist and responses to program related questions are developed by Solicitation Team . Contract Unit-Mentor role is CONSULT or NO ROLE, determined on a case-by-case basis.
Solicitation Team
4b.10 | Prepare/post Q&A, and prepare/post addendum (if needed) | Contract Unit-Specialist |  | Contract Unit-Mentor | Program/Project Manager | IN MOST CASES, Contract Unit-Specialist is RESPONSIBLE for this step, and Program/Project Manager role is INFORM. These roles may be reversed in limited cases, and in consideration of Risk Triage and Grant Framework, currently under development. Contract Unit-Mentor role is CONSULT or NO ROLE, determined on a case-by-case basis.
|  | Program/Project Manager |  |  | Contract Unit-Specialist
Proposer/Applicant
4b.11 | Review Q&A, prepare proposal and submit | Proposer/Applicant
4c. | Part 4c. Evaluate responses
4c.1 | Pull proposals | Contract Unit-Specialist
4c.2 | Evaluate Pass / Fail requirements | Contract Unit-Specialist
4c.3 | Share continuing proposals with Evaluation Team - provide guidance | Contract Unit-Specialist |  |  | Program/Project Manager
Evaluation Team
4c.4 | Complete and sign conflict of interest form | Program/Project Manager |  |  | Contract Unit-Specialist | Evaluation Team may be same or different than Solicitation Team
Evaluation Team
4c.5 | Individuals separately evaluate and score proposals and return | Program/Project Manager |  |  | Contract Unit-Specialist
Evaluation Team
4c.6 | Evaluate fee schedules / cost proposals | Contract Unit-Specialist |  | Contract Unit-Mentor
4c.7 | Compile results | Contract Unit-Specialist |  | Contract Unit-Mentor
4c.8 | Meet to finalize evaluation and confirm high score/s | Program/Project Manager
Contract Unit-Specialist
Evaluation Team
4d. | Part 4d. Negotiate
4d.1 | If needed, prepare for negotiations and negotiate | Contract Unit-Specialist |  | Contract Unit-Mentor |  | Program/Project Manager role may be CONSULT or RESPONSIBLE, determined on a case-by-case basis. Contract Unit-Mentor role is CONSULT or NO ROLE, determined on a case-by-case basis.
|  | Proposer/Applicant |  | Program/Project Manager
Program/Project Manager
4e. | Part 4e. Award
4e.1 | Award in SWIFT | Contract Unit-Specialist |  |  | Program/Project Manager
5 | Notification (approach and timing may vary depending on program) | Contract Unit-Specialist |  | Program/Project Manager |  | Program/Project Manager role may be CONSULT or RESPONSIBLE, determined on a case-by-case basis.
Program/Project Manager
5 | Part 5. Prepare Contract, Grant or Amendment
5.1 | Develop Contract/Grant project plan per template | Program/Project Manager |  | Technical Staff |  | Technical Staff role is CONSULT or NO ROLE, determined on a case-by-case basis.
Contract Unit-Specialist
5.2 | Develop/refine workplan, budget, Gantt & Cert | Program/Project Manager | Division Leadership | Technical Staff | Division Leadership | Contractor/Grantee role is RESPONSIBLE or CONSULT, determined on a case-by-case basis. Technical Staff role is CONSULT or NO ROLE, determined on a case-by-case basis. Division Leadership role is APPROVE, CONSULT or INFORM, determined on a case-by-case basis.
Division Leadership
|  | Contractor/Grantee |  | Contract Unit-Specialist
Contractor/Grantee
5.3 | Division level approval of workplan using checklist (WSD requires) |  | Division Leadership | Program/Project Manager |  | Need for Division Leadership approval is determined by Division Leadership. Program/Project Manager and Technical Staff roles may be CONSULT or NO ROLE, determined on a case-by-case basis.
Technical Staff
5.4 | Determine, develop necessary Contract/Grant documents | Contract Unit-Specialist |  | Dept. of Admin. |  | Dept. of Admin role is CONSULT or NO ROLE, determined on a case-by-case basis.
5.6 | Review & route Cert (if req'd) | Contract Unit-Specialist |  |  | Program/Project Manager
5.7 | Approve and sign Cert (if req'd) |  | PCA Signer |  | Program/Project Manager
|  |  | Dept. of Admin. |  | Contract Unit-Specialist
5.8 | Peer review of complete Contract/Grant package (per checklist), revise | Program/Project Manager |  | Contract Unit-Peer reviewer |  | Program/Project Manager role is RESPONSIBLE or NO ROLE, determined on a case-by-case basis.
Contract Unit-Specialist
6 | Part 6. Route for Signatures
6.1 | Determine if Contract/Grant will be routed for signatures within SWIFT or not. (If not, get approval from Contract Supervisor) | Contract Unit-Specialist | Contract Unit-Supervisor
6a. | Part 6a. Route Outside of SWIFT
6a.1 | Place final complete Contract/Grant package in Routing In folder in Contracts X Drive. | Contract Unit-Specialist
6a.2 | Create SWIFT shell, encumber funds | Purchaser |  |  | Contract Unit-Specialist
6a.3 | Email contract to Contractor/Grantee | Purchaser |  |  | Program/Project Manager
Contract Unit-Specialist
6a.4 | Print, sign or not, scan, return | Contractor/Grantee | Contractor/Grantee |  | Purchaser | Contractor/Grantee role is both RESPONSIBLE and APPROVE.
6a.5 | Verify encumbrance, print for PCA signature, update CRDB | Purchaser |  |  | Contract Unit-Specialist | Program/Project Manager role is INFORM or NO ROLE, determined on a case-by-case basis.
Program/Project Manager
6a.6 | PCA signature |  | PCA Signer |  | Program/Project Manager
Contract Unit-Specialist
6a.7 | Notify CS that Contract/Grant has been signed by PCA | Purchaser |  |  | Contract Unit-Specialist
6a.7 | If Interagency Agreement, Annual Plan Agreement or Grant, notify (PM to notify) Contractor/Grantee to begin work | Program/Project Manager |  |  | Program/Project Manager | Program/Project Manager role is RESPONSIBLE or INFORM, determined on a case-by-case basis.
|  | Contract Unit-Specialist |  |  | Contractor/Grantee
6a.8 | If Interagency Agreement, Annual Plan Agreement or Grant, begin work | Contractor/Grantee |  |  | Program/Project Manager
6a.9 | Send to Admin--if amendment, add docs to complete package | Purchaser |  |  | Contract Unit-Specialist | Program/Project Manager role is INFORM or NO ROLE, determined on a case-by-case basis.
Dept. of Admin.
Program/Project Manager
6a.10 | Administration signature (not required on Interagency Agreement, Annual Plan Agreement or Grant) |  | Dept. of Admin. |  | Program/Project Manager
Purchaser
Contract Unit-Specialist
6a.11 | If NOT Interagency Agreement, Annual Plan Agreement or Grant, notify (PM to notify) vendor to begin work | Program/Project Manager |  |  | Program/Project Manager | Program/Project Manager role is RESPONSIBLE or INFORM, determined on a case-by-case basis.
|  | Contract Unit-Specialist |  |  | Contractor/Grantee
6a.12 | Pick up signed Contract from Admin | Purchaser
6b. | Part 6b. Route Within SWIFT
6b.1 | Create shell, notify purchaser w/ encumbrance report | Contract Unit-Specialist |  |  | Purchaser
6b.2 | Encumber funds | Purchaser |  |  | Contract Unit-Specialist
6b.3 | Resolve issues, if any arise upon encumbrance | Program/Project Manager |  |  | Contract Unit-Specialist
|  | Fiscal Coordinator |  |  | Purchaser
6b.4 | Upload into SWIFT & route | Contract Unit-Specialist
6b.5 | If PT, PCA approves (this SWIFT step is not the same as signing a Contract/Grant) |  | PCA Signer |  | Contract Unit-Specialist
6b.6 | Route to Contractor/Grantee | Contract Unit-Specialist |  |  | Program/Project Manager | Program/Project Manager role is INFORM or NO ROLE, determined on a case-by-case basis.
6b.7 | Contractor/Grantee review and sign contract |  | Contractor/Grantee
6b.8 | Verify encumbrance | Purchaser
6b.8 | PCA sign Contract/Grant |  | PCA Signer
6b.9 | Admin sign Contract, if not Grant, Annual Plan Agreement or Interagency Agreement |  | Dept. of Admin.
6b.10 | Receive execution notice |  |  |  | Contract Unit-Specialist
6b.11 | Notify PM & Contractor/Grantee (who?) | Contract Unit-Specialist |  |  | Program/Project Manager
Contractor/Grantee
6b.12 | Send docs to Contractor/Grantee, PM & purchaser; update CRDB | Contract Unit-Specialist |  |  | Program/Project Manager
Contractor/Grantee
7 | Part 7. Record Management
7a. | Part 7a. If Routed Outside of SWIFT
7a.1 | Scan into OnBase; put hard copy in Fiscal File | Contract Unit-New CS |  |  | Program/Project Manager | Responsibility for this task is either Contract Unit-New CS role or Purchaser role - standard yet to be determined.
Purchaser
7a.2 | Update CRDB | Contract Unit-Specialist |  |  |  | Responsibility for this task is either Contract Unit-Specialist role or Purchaser role - standard yet to be determined.
Purchaser
7b. | Part 7b. If Routed Within SWIFT
7b.1 | Scan into OnBase; put hard copy in Fiscal File | Contract Unit-New CS |  |  | Program/Project Manager | Responsibility for this task is either Contract Unit-New CS role or Purchaser role - standard yet to be determined.
Purchaser
X:\Agency_Files\Process Documentation\Agency-wide Processes\Contracts CI 2014\Implementation Plan\1 Roles and Responsibilities\ContractandRFPDevelopmentRoles-042215.xlsx
Program/Project Manager
Contract Unit
Division Leadership
Technical Staff
Contractor/Grantee
Purchaser
PCA Approver/Signer
Dept. of Administration
Fiscal Coordinator

## RFP roles
RFP Roles (12/15/14 draft)
TASK | Responsible | Consult | Inform | Approve | Notes
| Responsible for the decision/task | Must be consulted by the responsible entity prior to a decision or as part of the task. Agreement not required. | Need to be informed of the final decision or task. No formal role in the decision or task. | Must approve a decision before it can be implemented or moving on to the next step.
Determine if RFP is required | Contract Specialist | Program/Project Manager
Division Leadership
Contract Unit Mentor
Part 4. Solicitation (if required)
Part 4a. Develop RFP
Create RFP Team | Program/Project Manager | RFP Team | Contract Specialist |  | RFP Team may include Division Leadership
Division Leadership
Sign confidentiality agreement | Program/Project Manager |  | Contract Specialist |  | Division Leadership must sign confidentiality agreement if they are to be informed or consulted
RFP Team
(Division Leadership?)
Discuss scope | Program/Project Manager | Contract Specialist
| RFP Team | (Division Leadership?)
Confirm if RFP will be posted in SWIFT or not, per standard | Contract Specialist | Program/Project Manager | RFP Team | Contract Supervisor | If out of SWIFT, Contract Supervisor must approve
Draft RFP scope and summary | Program/Project Manager | RFP Team
Contract Specialist
(Division Leadership?)
Draft RFP template and sample contract | Contract Specialist | (Contract Unit Mentor?) | (RFP Team ?)
|  | (Program/Project Manager?) | (Division Leadership?)
Compile list of potential vendors to be contacted. | Program/Project Manager | Contract Specialist
| RFP Team | (Division Leadership?)
Final RFP review by RFP Team | Program/Project Manager |  | Contract Specialist | (Division Leadership?) | Division Leadership approval at discretion of Division Leadership
RFP Team
Part 4b. Approve and Post RFP
Upload complete RFP packet into SWIFT, unless alternative approved | Contract Specialist
Mentor approval |  | Contract Specialist | Program/Project Manager | Contract Unit Mentor
PCA Approver/Signer approval |  |  | Program/Project Manager | PCA Approver/Signer
Contract Specialist
If PT RFP, Dept. of Administration approval |  |  | Program/Project Manager | Dept. of Administration
Contract Specialist
Post on Web, and SWIFT, if applicable | Contract Specialist |  | Program/Project Manager
Proposer/Applicant
Communicate on program website and other sources, if desired | Program/Project Manager | Contract Specialist | Proposer/Applicant
Review proposal and submit questions, if any. | Proposer/Applicant |  | Program/Project Manager
Contract Specialist
Receive questions, share w RFP Team and develop responses | Contract Specialist |  | Program/Project Manager
| (Program/Project Manager?) |  | (Contract Specialist)
Prepare Q&A / addendum and post | Contract Specialist (Program/Project Manager?) | Contract Unit Mentor? | Program/Project Manager
(Contract Specialist)
Proposer/Applicant
Review Q&A, prepare proposal and submit | Proposer/Applicant
Part 4c. Evaluate responses
Pull proposals | Contract Specialist
Evaluate Pass / Fail requirements | Contract Specialist
Share continuing proposals with Evaluation Team - provide guidance | Contract Specialist |  | Program/Project Manager
Evaluation Team
Complete and sign conflict of interest form | Program/Project Manager |  | Contract Specialist |  | Evaluation Team may be same or different than RFP Team
Evaluation Team
Individuals separately evaluate and score proposals and return | Program/Project Manager |  | Contract Specialist
Evaluation Team
Evaluate fee schedules / cost proposals | Contract Specialist | Contract Unit Mentor
Compile results | Contract Specialist | Contract Unit Mentor
Meet to finalize evaluation and confirm high score/s | Program/Project Manager
Contract Specialist
Evaluation Team
Part 4d. Negotiate
If needed, prepare for negotiations and negotiate | Contract Specialist | (Contract Unit Mentor?)
| Proposer/Applicant | (Program/Project Manager?)
(Program/Project Manager?)
Part 4e. Award
Award in SWIFT | Contract Specialist |  | Program/Project Manager
Notification (approach and timing may vary depending on program) | Contract Specialist | Program/Project Manager
(Program/Project Manager?)
Program/Project Manager
Contract Specialist
Division Leadership
RFP Team
Proposer/Applicant
PCA Approver/Signer
Dept. of Administration